## Product Backlog
Epic | Feature | User Story | Description | Priority | Status | Version | Story Points | Jira Type
Core AI Generation | Generate test from comment | As a QA engineer I want to generate tests from comments so I can automate faster | Right click comment → generate Playwright test | High | Done | V1 | 5 | Story
Core AI Generation | Excel test generation | As a QA engineer I want to convert Excel test cases into automation | Upload Excel → generate test methods | High | Done | V1 | 8 | Story
Core AI Generation | AI Tool Window | As a QA engineer I want a tool window to generate tests using prompts | IntelliJ side panel for AI generation | High | Done | V1 | 5 | Story
AI Improvements | Prompt optimization | Improve AI prompts for more accurate tests | Improve prompt engineering for frameworks | High | In Progress | V2 | 3 | Task
Multi Framework | Framework selector | As a QA engineer I want to choose framework | Playwright / Selenium / Cypress dropdown | High | To Do | V2 | 8 | Story
Multi Framework | Selenium support | Generate Selenium Java tests | AI generates Selenium WebDriver tests | Medium | To Do | V2 | 5 | Story
Multi Framework | Cypress support | Generate Cypress tests | AI generates Cypress JS tests | Medium | To Do | V2 | 5 | Story
AI Productivity | Page object generator | Generate Page Object classes | Convert selectors into Page Objects | Medium | To Do | V2 | 8 | Story
AI Productivity | Locator generator | Generate stable locators | Right click HTML → generate locator | Medium | To Do | V2 | 5 | Story
AI Productivity | Test fixer | Fix failing tests using AI | AI analyzes error logs and updates locator | High | Future | V3 | 8 | Story
API Testing | API test generation | Generate API tests from OpenAPI | Upload swagger → generate RestAssured tests | Medium | Future | V3 | 8 | Story
AI UX | Streaming generation | Stream AI response in editor | Show generated code gradually | Medium | Future | V3 | 5 | Task
Settings | Plugin settings page | Allow user to configure API key and framework | IntelliJ settings page | High | To Do | V2 | 3 | Story

## Release Roadmap
Version | Release Goal | Features
V1 | Initial Release | Comment generation, Excel parsing, Tool Window
V2 | Multi framework support | Framework selector, Selenium, Cypress, Page Object generation
V3 | AI productivity suite | Test fixer, API generation, streaming

## Status Summary
Status | Count
Done | 3
In Progress | 1
To Do | 5
Future | 4